### Project Evaluation Report: Jahangirnagar University Student Information System (JUSIS)

#### Part A: Programme Context

1. Programme vs. Project Justification JUSIS is not just a single project; it is a strategic programme. It consists of a group of projects that are managed in a co-ordinated way to gain benefits that would not be possible were the projects to be managed independently. Two sub-projects under this programme are:

- Admission Module: For online applications and enrollment.

- Examination Module: For digital grading and transcript generation.

2. Programme Mandate The initial planning document is the Programme Mandate. For JUSIS, the mandate is to deliver a new capability to centrally manage all student records, replacing manual files. This perfectly fits JU's organizational goal of becoming a "Digital University".

3. Vision Statement & Blueprint

- Vision Statement: JUSIS will provide the new capability to seamlessly manage academic and administrative data in real-time.

- Blueprint: To obtain this capability, the changes to be made include installing new central servers, upgrading campus networks, and re-training administrative staff.

#### Part B: Benefits Management Plan

Providing an organization with a capability does not guarantee that this will provide benefits envisaged. Here are 6 expected benefits for JUSIS:

| Category | Example Benefit for JUSIS |
| --- | --- |
| A) Quantified and Valued | Automating transcript generation saves 3 admin staff 10 hours/week. Value = 3 staff × 10hrs × BDT 500/hr × 52 weeks = BDT 780,000/year. |
| A) Quantified and Valued | Paperless forms reduce printing costs. Value = 15,000 applicants × BDT 50 = BDT 750,000/year. |
| B) Quantified but not Valued | A 50% decrease in manual data entry errors across all departments. |
| B) Quantified but not Valued | A 60% reduction in student wait times for registration inquiries. |
| C) Identified but not easily Quantified | Improved public reputation for the university due to a modern digital system. |
| C) Identified but not easily Quantified | A more motivated workforce as staff are freed from repetitive manual filing. |

Benefits Monitoring: Benefits management has to be outside the project because the project will have been completed. The Programme Director will be responsible to monitor achievement of benefits post-launch.

#### Part C: Cost-Benefit Analysis & Cash Flow Forecasting

1. Cash Flow Table

| Year | Costs (BDT) | Benefits (BDT) | Cash-flow (BDT) | Accumulated Net (BDT) |
| --- | --- | --- | --- | --- |
| 0 | 4,500,000 | 0 | -4,500,000 | -4,500,000 |
| 1 | 600,000 | 800,000 | 200,000 | -4,300,000 |
| 2 | 600,000 | 1,200,000 | 600,000 | -3,700,000 |
| 3 | 600,000 | 1,800,000 | 1,200,000 | -2,500,000 |
| 4 | 600,000 | 2,200,000 | 1,600,000 | -900,000 |
| 5 | 600,000 | 2,600,000 | 2,000,000 | 1,100,000 |

Note: Year 0 represents all the costs before system is operation. Cash-flow is value of income less outgoing.

2. Total Net Profit Net profit is the value of all the cash-flows for the lifetime of the application.

- Total Net Profit = (-4.5M + 200k + 600k + 1.2M + 1.6M + 2.0M) = BDT 1,100,000.

3. Payback Period This is the time it takes to start generating a surplus of income over outgoings.

- At the end of Year 4, the deficit is BDT 900,000.

- Year 5 cash flow is BDT 2,000,000.

- Remaining time = (900,000 / 2,000,000) = 0.45 years.

- 0.45 years × 12 months = 5.4 months.

- Result: 4 years and 5 months (approx).

4. Return on Investment (ROI) Formula: (Average annual profit / Total investment) × 100.

- Average annual profit = 1,100,000 / 5 = BDT 220,000.

- ROI = (220,000 / 4,500,000) × 100 = 4.88%.

#### Part D: Net Present Value (NPV) & Internal Rate of Return (IRR)

1. Calculate NPV Discount factor = $1/(1+r)^t$, where $r = 0.12$.

| Year | Cash-flow (BDT) | Discount factor | Discounted cash flow (BDT) |
| --- | --- | --- | --- |
| 0 | -4,500,000 | 1.0000 | -4,500,000 |
| 1 | 200,000 | 0.8929 | 178,571 |
| 2 | 600,000 | 0.7972 | 478,316 |
| 3 | 1,200,000 | 0.7118 | 854,136 |
| 4 | 1,600,000 | 0.6355 | 1,016,830 |
| 5 | 2,000,000 | 0.5674 | 1,134,854 |
| Total |  |  | NPV = -837,293 |

- Conclusion: The project is not financially worthwhile under a 12% discount rate over 5 years. The negative NPV means the returns are lower than what the university could earn by simply investing the money elsewhere at 12% interest.

2. Interpret IRR

- Internal rate of return (IRR) is the discount rate that would produce an NPV of 0 for the project.

- If the IRR is 18% and the borrowing rate is 12%, the university should proceed. This means the project generates an 18% return, easily covering the 12% cost of borrowing the funds, ultimately creating financial value.

#### Part E: Risk Evaluation & Decision Analysis

1. Project Risk Matrix We can draw up a project risk matrix to assess risks.

| Risk | Likelihood | Importance (Impact) |
| --- | --- | --- |
| 1. Resistance from administrative staff | High (H) | High (H) |
| 2. Legacy data migration errors | Medium (M) | High (H) |
| 3. Development budget exceeded | Medium (M) | Medium (M) |
| 4. System response time targets not met | High (H) | Low (L) |

- Mitigation Strategy (For Risk 1): A project may fail not through poor management but because it should never have been started. To avoid this, we will ensure end-users are heavily involved from the beginning and provide thorough training programs so they accept the new system rather than resist it.

2. Decision Tree Analysis

Assuming a standardized financial benefit of BDT 10,000,000 for a successful system.

- Build (Local Developers): Cost = 3M, Success = 80%.

  - EMV = (0.8 × 10,000,000) - 3,000,000 = BDT 5,000,000

- Buy (Off-the-shelf): Cost = 5M, Success = 95%.

  - EMV = (0.95 × 10,000,000) - 5,000,000 = BDT 4,500,000

- Recommendation: The university should choose to Build. Although buying off-the-shelf is safer, building in-house has a higher Expected Monetary Value (EMV). Projects with the highest potential returns are often the most risky.