## Project Gantt Chart
WBS | Module Name | Main Stakeholder | Duration (Days) | From Date | To Date | 01-Jul | 02-Jul | 03-Jul | 04-Jul | 05-Jul | 06-Jul | 07-Jul | 08-Jul | 09-Jul | 10-Jul
1 | Requirement Analysis & Planning | Manager, System Analyst and University Authority | 1 | 01-Jul-2026 | 01-Jul-2026
2 | Authentication System (Login + Role Based Access) | Manager and System Analyst | 0.5 | 01-Jul-2026 | 01-Jul-2026
3 | Student Registration / Admission | Admission Office, System Analyst | 1 | 02-Jul-2026 | 02-Jul-2026
4 | Student Profile Management | Student Affairs Office, System Analyst | 0.5 | 02-Jul-2026 | 02-Jul-2026
5 | Syllabus & Course Management | Academic Office, Faculty Members | 1 | 03-Jul-2026 | 03-Jul-2026
6 | Credit System Management | Academic Office | 0.5 | 04-Jul-2026 | 04-Jul-2026
7 | Academic Progress Tracking | Academic Office, Faculty Members | 1 | 04-Jul-2026 | 05-Jul-2026
8 | Exam Management (Mid/Final/Quiz) | Examination Office, Faculty Members | 1.5 | 05-Jul-2026 | 06-Jul-2026
9 | Result Information System | Examination Office | 1 | 07-Jul-2026 | 07-Jul-2026
10 | Reporting Module | University Management, Registrar Office | 1 | 08-Jul-2026 | 08-Jul-2026